## Sheet1
Task Name | Start | Finish | Resource Names
Scope | Mon 1/30/12 | Mon 2/6/12
Define Project Scope | Mon 1/30/12 | Mon 1/30/12 | Churk Y. Leung
Define Development Tools and Hosting Environment | Mon 1/30/12 | Mon 1/30/12 | Churk Y. Leung
Define Roles and Responsibility | Mon 2/6/12 | Mon 2/6/12 | Vladimir Velev
Define Deliverables | Mon 2/6/12 | Mon 2/6/12 | Vladimir Velev
Scope Complete | Mon 2/6/12 | Mon 2/6/12
Analysis/Software Requirements | Mon 2/13/12 | Mon 2/27/12
Team Discussion and Software Requirements Gathering | Mon 2/20/12 | Mon 2/27/12 | The iTeam
Produce SRS with Ucase and Mockups | Mon 2/20/12 | Mon 2/27/12 | Vladimir Velev,Laurene Assayah
Team Review software specifications | Sun 2/26/12 | Fri 3/16/12 | The iTeam
Incorporate Changes into Schedule | Mon 2/13/12 | Fri 3/23/12 | Quan Pham
Develop delivery timeline | Mon 2/20/12 | Fri 3/30/12 | Vladimir Velev
Analysis complete | Mon 2/27/12 | Mon 2/27/12
Design | Mon 2/13/12 | Mon 3/19/12
Review preliminary software specifications | Mon 2/13/12 | Mon 3/12/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Develop functional specifications - front end | Tue 2/14/12 | Fri 3/23/12 | Vanya Dineva,Quan Pham
Develop functional specifications - back end | Sat 2/18/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels
Review functional specifications | Mon 2/27/12 | Fri 4/27/12 | Laurene Assayah,Vladimir Velev
Design complete | Fri 4/27/12 | Fri 4/27/12
Development | Mon 2/27/12 | Fri 4/27/12
Identify modular/tiered design parameters | Mon 2/27/12 | Mon 3/19/12 | Churk Y. Leung
Develop code | Mon 2/27/12 | Fri 4/20/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vanya Dineva
Developer testing (primary debugging) | Mon 3/5/12 | Fri 4/27/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Development complete | Fri 4/27/12 | Fri 4/27/12
Testing | Mon 4/2/12 | Mon 4/16/12
Develop test plans | Mon 4/2/12 | Mon 4/9/12 | Vanya Dineva,Laurene Assayah
Review test plans | Mon 4/9/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vladimir Velev
Implement Test Plans | Mon 4/9/12 | Mon 4/16/12 | Vanya Dineva,Laurene Assayah
Unit testing complete | Mon 4/16/12 | Mon 4/16/12
Documentation | Mon 2/6/12 | Fri 4/27/12
Project Proposal | Mon 2/6/12 | Mon 4/9/12 | Churk Y. Leung
SPMP Document | Mon 2/6/12 | Fri 4/27/12 | Quan Pham,Vladimir Velev
SQAP Document | Mon 2/6/12 | Fri 4/27/12 | Laurene Assayah,Vanya Dineva
SCMP Document | Mon 2/6/12 | Fri 4/27/12 | Jonathan Reimels
Develop Project Schedule | Mon 2/6/12 | Fri 4/27/12 | Quan Pham
Develop user manuals | Mon 2/6/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Review all user documentation | Mon 4/9/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Incorporate user documentation feedback | Mon 4/9/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Documentation complete | Mon 4/30/12 | Mon 4/30/12
Final Presentation | Mon 4/23/12 | Mon 4/30/12
Determine final presentation strategy | Mon 4/30/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Prepare Powerpoint Slide & Poster | Mon 4/23/12 | Mon 4/30/12 | Quan Pham
Presentation complete | Mon 4/30/12 | Mon 4/30/12
Post Presentation Review | Mon 4/30/12 | Mon 4/30/12
Document lessons learned | Mon 4/30/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Create software maintenance team | Mon 4/30/12 | Mon 4/30/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Popst presentation preview complete | Mon 4/30/12 | Mon 4/30/12
Deliverables | Mon 1/30/12 | Mon 4/30/12
Week 1 Team Report | Mon 1/30/12 | Mon 1/30/12 | Vladimir Velev
Week 2 Team Report | Mon 2/6/12 | Mon 2/6/12 | Vladimir Velev
Week 3 Team Report | Mon 2/13/12 | Mon 2/13/12 | Vladimir Velev
Week 4 Team Report | Mon 2/20/12 | Mon 2/20/12 | Vladimir Velev
Week 5 Team Report | Mon 2/27/12 | Mon 2/27/12 | Vladimir Velev
Week 6 Team Report | Mon 3/5/12 | Mon 3/5/12 | Vladimir Velev
Week 7 Team Report | Mon 3/19/12 | Mon 3/19/12 | Vladimir Velev
Week 8 Team Report | Mon 3/26/12 | Mon 3/26/12 | Vladimir Velev
Week 9 Team Report | Mon 4/2/12 | Mon 4/2/12 | Vladimir Velev
Week 10 Team Report | Mon 4/9/12 | Mon 4/9/12 | Vladimir Velev
Week 11 Team Report | Mon 4/16/12 | Mon 4/16/12 | Vladimir Velev
Week 12 Team Report | Mon 4/23/12 | Mon 4/23/12 | Vladimir Velev
Week 13 Team Report | Mon 4/30/12 | Mon 4/30/12 | Vladimir Velev
PHASE I | Mon 2/13/12 | Mon 2/13/12 | The iTeam
PHASE II | Mon 2/27/12 | Mon 2/27/12 | The iTeam
PHASE III | Mon 3/26/12 | Mon 3/26/12 | The iTeam
FINAL PRESENTATION | Mon 4/30/12 | Mon 4/30/12 | The iTeam
Delivarables complete | Mon 4/30/12 | Mon 4/30/12