## Slide 1: iBudget (Final Presentation)
Keeping your information private while letting us make sense of your expenses.
The iTeam:
Churk Leung
Vanya Dineva
Quan Pham
Jonathan Reimels
Laurene Assayah
Vladimir Velev

## Slide 2: What is iBudget?
A web-based personal financial management service designed to:
Keep track of all your financial accounts into one place
Allow you to set a budget
Manage individual transactions

## Slide 3: Competition: Mint.com
See all accounts
Auto categorization
Timely alerts to email and phone
Helpful graphs

## Slide 4: Competitive Advantage
iBudget
Does NOT require:
A secure connection to a financial institution
Login credentials to a financial institution
Requires:
Account credentials to financial institutions

## Slide 5: Project Organization Process Model: Unified Process
 | Phase 1 | Phase 2 | Phase 3 | Phase 4
Planning |  |  |  | 
Requirements Analysis |  |  |  | 
Implementation |  |  |  | 
Testing |  |  |  | 

## Slide 6: Project Organization
Organizational Structure

## Slide 7: Management Process: Management Objectives and Priorities
The completion of the project on time before the end of the school semester
Meeting a degree of quality as specified at the beginning of the project
Complete as many requirements as were planned at the beginning of the project

## Slide 8: Management Process: Risk Management
# | Risk Title | Likelihood to Occur 1-10 | Impact 1-10 | Retirement Cost 1-10 | Priority | Retirement or Mitigation Plan | Responsible Engineer | Target Completion Date
1 | Requirements Inflation | 3 | 8 | 2 | 48 | Add additional features depending on time. | All | 04/02
2 | Poor Productivity | 7 | 10 | 10 | 40 | Keep developers engaged and motivated. | Project Leader | 04/30
3 | Shortfalls in 3rd party software | 4 | 3 | 6 | 336 | Analyze software capabilities in advance. | TBD | 04/15
4 | Insufficient time | 8 | 9 | 5 | 30 | Follow schedule. | Project Leader | 04/30
5 | Unforeseen software defects | 7 | 7 | 5 | 45 | Allocate enough time for defect resolution. | All | 04/16

## Slide 9: Management Process: Monitoring and controlling mechanism
Weekly project meetings on Monday @ 5 PM
Weekly reports completed by each team member

## Slide 10: Management Process: Staffing Plan
Name | Team Leader | CM Leader | QA Leader | Requirement Management Leader | Design Leader | Implementation Leader
Vladimir Velev | X |  |  |  |  | 
Jonathan Reimels |  | X |  |  |  | 
Vanya Dineva |  |  | X |  |  | 
Laurene Assayah |  |  |  | X |  | 
Churk Leung |  |  |  |  | X | 
Quan Pham |  |  |  |  |  | X

## Slide 11: Budget and resource allocation
Estimate LOC:
FP = (∑UFP_i)*GCF
UFP_i = 3 (EI) + 4 (EO) + 3 (EIN) + 7 (ILF) + 5 (ELF) = 22
GCF = 0.65 + 0.01 * 42 = 1.07
FP = 23.54
LOC = 23.54 * (600 LOC/FP) = 14 KLOC
COCOMOI:
Effort Applied (E) = 3.0 * (14)^1.12 = 57 man-months
Development Time (D) = 2.5 * (57)^0.38 = 11 months
People required (P) = 57/11 = 6

## Slide 12: Schedule
Design | Mon 2/13/12 | Mon 3/19/12 | 
Review preliminary software specifications | Mon 2/13/12 | Mon 3/12/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Develop functional specifications - front end | Tue 2/14/12 | Fri 3/23/12 | Vanya Dineva,Quan Pham
Develop functional specifications - back end | Sat 2/18/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels
Review functional specifications | Mon 2/27/12 | Fri 4/27/12 | Laurene Assayah,Vladimir Velev
Design complete | Fri 4/27/12 | Fri 4/27/12 | 
Development | Mon 2/27/12 | Fri 4/27/12 | 
Identify modular/tiered design parameters | Mon 2/27/12 | Mon 3/19/12 | Churk Y. Leung
Develop code | Mon 2/27/12 | Fri 4/20/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vanya Dineva
Developer testing (primary debugging) | Mon 3/5/12 | Fri 4/27/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Development complete | Fri 4/27/12 | Fri 4/27/12 | 
Testing | Mon 4/2/12 | Mon 4/16/12 | 
Develop test plans | Mon 4/2/12 | Mon 4/9/12 | Vanya Dineva,Laurene Assayah
Review test plans | Mon 4/9/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vladimir Velev
Implement Test Plans | Mon 4/9/12 | Mon 4/16/12 | Vanya Dineva,Laurene Assayah
Unit testing complete | Mon 4/16/12 | Mon 4/16/12 | 

## Slide 13: Configuration Management and Version Control
Google Project Hosting
  Contain all project documents
Configuration summary will be managed in the project wiki
  http://code.google.com/p/cs679-b1-class-project/w/list
svn (from Google Project Hosting)
  Used to control versions of all project documents

## Slide 14: Software Quality

## Slide 16: System Architecture

## Slide 17: Design Patterns
Factory
Singleton

## Slide 18: Data Description
A = Auto Increment; N = NOT NULL; P = Primary Key
U = Unique; I = Indexed; D = Has default value assigned
F = Foreign Key

## Slide 19: Human Interface Design

## Slide 20: Human Interface Design

## Slide 21: Human Interface Design

## Slide 22: Human Interface Design

## Slide 23: Human Interface Design

## Slide 24: Online Demonstation
http://ibudget.simplefunctions.com
We each take turn to show the pages or functionalities that we worked on.

## Slide 25: Source Code
We can pick out section of source code that we want to show

## Slide 26: Q & A