## Slide 1: iBudget (Final Presentation)
Keeping your information private while letting us make sense of your expenses.
The iTeam:
Churk Leung
Vanya Dineva
Quan Pham
Jonathan Reimels
Laurene Assayah
Vladimir Velev

## Slide 2: What is iBudget?
A web-based personal financial management service designed to:
Keep track of all your financial accounts into one place
Allow you to set a budget
Manage individual transactions

## Slide 3: Competition: Mint.com
See all accounts
Auto categorization
Timely alerts to email and phone
Helpful graphs

## Slide 4: Competitive Advantage
iBudget
Does NOT require:
A secure connection to a financial institution
Login credentials to a financial institution
Requires:
Account credentials to financial institutions

## Slide 5: Project Organization Process Model: Unified Process
 | Phase 1 | Phase 2 | Phase 3 | Phase 4
Planning |  |  |  | 
Requirements Analysis |  |  |  | 
Implementation |  |  |  | 
Testing |  |  |  | 

## Slide 6: Project Organization
Organizational Structure

## Slide 7: Management Process: Management Objectives and Priorities
The completion of the project on time before the end of the school semester
Meeting a degree of quality as specified at the beginning of the project
Complete as many requirements as were planned at the beginning of the project

## Slide 8: Management Process: Risk Management
# | Risk Title | Likelihood to Occur 1-10 | Impact 1-10 | Retirement Cost 1-10 | Priority | Retirement or Mitigation Plan | Responsible Engineer | Target Completion Date
1 | Requirements Inflation | 3 | 8 | 2 | 48 | Add additional features depending on time. | All | 04/02
2 | Poor Productivity | 7 | 10 | 10 | 40 | Keep developers engaged and motivated. | Project Leader | 04/30
3 | Shortfalls in 3rd party software | 4 | 3 | 6 | 336 | Analyze software capabilities in advance. | TBD | 04/15
4 | Insufficient time | 8 | 9 | 5 | 30 | Follow schedule. | Project Leader | 04/30
5 | Unforeseen software defects | 7 | 7 | 5 | 45 | Allocate enough time for defect resolution. | All | 04/16

## Slide 9: Management Process: Monitoring and controlling mechanism
Weekly project meetings on Monday @ 5 PM
Weekly reports completed by each team member

## Slide 10: Management Process: Staffing Plan
Name | Team Leader | CM Leader | QA Leader | Requirement Management Leader | Design Leader | Implementation Leader
Vladimir Velev | X |  |  |  |  | 
Jonathan Reimels |  | X |  |  |  | 
Vanya Dineva |  |  | X |  |  | 
Laurene Assayah |  |  |  | X |  | 
Churk Leung |  |  |  |  | X | 
Quan Pham |  |  |  |  |  | X

## Slide 11: Budget and resource allocation
Estimate LOC:
FP = (∑UFP_i)*GCF
UFP_i = 3 (EI) + 4 (EO) + 3 (EIN) + 7 (ILF) + 5 (ELF) = 22
GCF = 0.65 + 0.01 * 42 = 1.07
FP = 23.54
LOC = 23.54 * (600 LOC/FP) = 14 KLOC
COCOMOI:
Effort Applied (E) = 3.0 * (14)^1.12 = 57 man-months
Development Time (D) = 2.5 * (57)^0.38 = 11 months
People required (P) = 57/11 = 6

## Slide 12: Time spent
Chart: 
| team member 1 | team member 2 | team member 3 | team member 4
Estimate: | 3.9757 | 5.9444 | 3.4688 | 4.6806
Actual: | 5.5382 | 3.9271 | 2.8438 | 3.4826

## Slide 13: Estimate vs Actual time spent
Chart: 
| Estimate: | Actual:
Row 26 | 19.434 | 16.6979

## Slide 14: Schedule
Design | Mon 2/13/12 | Mon 3/19/12 | 
Review preliminary software specifications | Mon 2/13/12 | Mon 3/12/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Develop functional specifications - front end | Tue 2/14/12 | Fri 3/23/12 | Vanya Dineva,Quan Pham
Develop functional specifications - back end | Sat 2/18/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels
Review functional specifications | Mon 2/27/12 | Fri 4/27/12 | Laurene Assayah,Vladimir Velev
Design complete | Fri 4/27/12 | Fri 4/27/12 | 
Development | Mon 2/27/12 | Fri 4/27/12 | 
Identify modular/tiered design parameters | Mon 2/27/12 | Mon 3/19/12 | Churk Y. Leung
Develop code | Mon 2/27/12 | Fri 4/20/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vanya Dineva
Developer testing (primary debugging) | Mon 3/5/12 | Fri 4/27/12 | Churk Y. Leung,Jonathan Reimels,Laurene Assayah,Quan Pham,Vanya Dineva,Vladimir Velev
Development complete | Fri 4/27/12 | Fri 4/27/12 | 
Testing | Mon 4/2/12 | Mon 4/16/12 | 
Develop test plans | Mon 4/2/12 | Mon 4/9/12 | Vanya Dineva,Laurene Assayah
Review test plans | Mon 4/9/12 | Mon 4/16/12 | Churk Y. Leung,Jonathan Reimels,Quan Pham,Vladimir Velev
Implement Test Plans | Mon 4/9/12 | Mon 4/16/12 | Vanya Dineva,Laurene Assayah
Unit testing complete | Mon 4/16/12 | Mon 4/16/12 | 

## Slide 15: Configuration Management and Version Control
Google Project Hosting
  Contain all project documents
Configuration summary will be managed in the project wiki
  http://code.google.com/p/cs679-b1-class-project/w/list
svn (from Google Project Hosting)
  Used to control versions of all project documents

## Slide 16: Requirements
Functional requirements:
Create an account
Log In / Log out
Edit profile information (password, name)
Upload CSV file
Handle budgets, categories and transactions

## Slide 17: Requirements
Non-Functional requirements:
Consistent look for different browsers
Enforce strong password
End of session
Maintainability, portability
Performance

## Slide 18: Use Case Diagram

## Slide 19: Software Quality
Each team member responsible for the quality of his/her work
Each project artifact was inspected by at least 2 reviewers before submission
Set of coding standards
Google code issue tracker used for issues

## Slide 20: Bug Tracking
Bugs will be tracked in the project wiki:
http://code.google.com/p/cs679-b1-class project/issues/list
Criteria
Example
ID
Type
Status
Priority
Owner
Summary
ID: 14
Type: Defect
Status: Accepted
Priority: Critical
Owner: churkl
Summary: Category on transactions are not loaded correctly

## Slide 21: What could we have done better?
Better task allocation
Pair programming
Unit tests

## Slide 22: System Architecture
Notes: The model manages the behavior and data of the application domain, responds to requests for information about its state (usually from the view), and responds to instructions to change state (usually from the controller). The model is not necessarily merely a database; the 'model' in MVC is both the data and the business/domain logic needed to manipulate the data.
The view renders the model into a form suitable for interaction, typically a user interface element. Multiple views can exist for a single model for different purposes.
The controller receives user input and initiates a response by making calls on model objects. A controller accepts input from the user and instructs the model and a view port to perform actions based on that input.

## Slide 23: Design Patterns
Factory
Singleton
Observer

## Slide 24: Data Description
A = Auto Increment; N = NOT NULL; P = Primary Key
U = Unique; I = Indexed; D = Has default value assigned
F = Foreign Key

## Slide 25: Human Interface Design

## Slide 26: Human Interface Design

## Slide 27: Human Interface Design

## Slide 28: Human Interface Design

## Slide 29: Human Interface Design

## Slide 30: Q & A

## Slide 31: Online Demonstation
http://ibudget.simplefunctions.com
We each take turn to show the pages or functionalities that we worked on.